## Project Planner
Nutrition Information Data Analysis Tool
[5 empty] | Period Highlight | 9 |  |  | Plan Duration | [5 empty] | Actual Start |  |  |  |  | % Complete |  |  |  |  | Actual (beyond plan) | [7 empty] | % Complete (beyond plan)
Activity No. and Name | Plan Start | Plan Duration | Actual Start | Actual Duration | Percent Complete | PERIODS
[6 empty] | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30 | 31 | 32 | 33 | 34 | 35 | 36 | 37 | 38 | 39 | 40 | 41 | 42 | 43 | 44 | 45 | 46 | 47 | 48 | 49 | 50 | 51 | 52 | 53 | 54 | 55 | 56 | 57 | 58 | 59 | 60
1.0 Initiating | 1 | 2 | 1 | 1 | 100%
1.1 Develop Project Overview | 1 | 1 | 1 | 1 | 100%
1.2 Develop Communication Plan | 1 | 1 | 1 | 1 | 100%
2.0 Planning | 2 | 15 | 1 | 16 | 100%
2.1 Develop System Vision Document | 2 | 2 | 1 | 2 | 100%
2.2 Establish WBS, Activity Estimate and Gantt | 2 | 3 | 2 | 7 | 100%
2.3 Define Project Requirements | 5 | 3 | 4 | 4 | 100%
2.4 Define System Architecture | 14 | 2 | 14 | 2 | 100%
2.5 Design UI Wireframes and Mockups | 9 | 3 | 8 | 4 | 100%
3.0 Execution | 17 | 21 |  |  | 0%
3.1 implement Food Search Feature | 17 | 7 |  |  | 0%
3.2 Implement Nutrition Breakdown Feature | 17 | 7 |  |  | 0%
3.3 implement Nutrition Range Filter Feature | 24 | 7 |  |  | 0%
3.4 Implement Nutrition Level Feature | 24 | 7 |  |  | 0%
3.5 Implement Recipe Builder | 24 | 7 |  |  | 0%
3.6 Testing | 31 | 7 |  |  | 0%
3.6.1 Unit Testing | 31 | 3 |  |  | 0%
3.6.2 User Acceptance Testing | 34 | 4 |  |  | 0%
4.0 Controlling | 1 | 44 | 1 | 44 | 20%
4.1 Project Monitoring | 1 | 44 | 1 | 44 | 20%
4.1.1 Weekly Team Check-In | 1 | 44 | 1 | 44 | 20%
4.1.2 Document Meeting Outcome | 1 | 44 | 1 | 44 | 20%
4.2 Performance Measurement | 17 | 28 |  |  | 0%
4.2.1 Task Tracking | 17 | 28 |  |  | 0%
4.2.2 Quality Checking | 17 | 28 |  |  | 0%
4.3 Change Management | 17 | 28 |  |  | 0%
4.3.1 Change Discussion | 17 | 28 |  |  | 0%
4.3.2 Change Implementation | 17 | 28 |  |  | 0%
5.0 Closing | 38 | 7 |  |  | 0%
5.1 Documentation | 38 | 6 |  |  | 0%
5.2 Final Performance Review | 44 | 1 |  |  | 0%
5.3 Project Closure | 44 | 1 |  |  | 0%
Activity 33 |  |  |  |  | 0%
Activity 34 |  |  |  |  | 0%
Activity 35 |  |  |  |  | 0%